## Implementation Chart
WCCUSD Arts Plan Implementation
2018-07-07
Focus Area I
Grade level | Section | Description | Phase I | Status | Phase II | Status | Phase III | Status
PK-6th | 1.1 | Re-instatement of Elementary Instrumental Music: 4th Grade to 6th Grade | 1.1.2: Increase Staffing by 1.0 FTE to achieve 5:1 ratio of schools to teacher. | Complete | 1.1.5: Expand music program to offer instruction on other instruments and to add instruction in the 3rd grade | Strings added to 4 elementary sites and to Helms Middle School; instruction beginning to reach into 3rd grade classes
|  |  | 1.1.3: Align Instruction with CCSS and provide grade level expectations for articulation to secondary grades | Ongoing | 1.1.6: Explore music integration in T-K – 2nd grades | Through Site Liaisons, Integration activities are diseminated to TK-2nd grade teachers; outside providers are in use at some sites.
|  |  | 1.1.4: Adopt District wide method books that incorporate connections to California Standards. | Complete | 1.1.7: Continue alignment of instruction | Teachers meet and refine goals and objectives to reflect developmental ages of students
|  |  | 1.1.1: Purchase additional instruments and supplies to support this program and to replace a worn and aging inventory | Ongoing | 1.1.8: Monitor and revise as needed | Feedback from instructors and site Principals drives program refinement.
| 1.2 | Develop plan for integration and implementation of arts learning in the elementary schools in connection with California Standards and the LCAP | 1.2.1: Determine level of arts instruction currently available in each elementary school | Dot Matrix by School Site available on the VAPA website | 1.2.4: Work with principals and teaching staff to outline specific curriculum areas and support implementation | ELA, Math, History, and Science all are enhanced by using the arts as a vehicle for instruction. Liaison Meetings and PD sessions support implementation
|  |  | 1.2.2: Provide support for teachers currently integrating art in their curriculum | Each Elementary and secondary school provided funding for supplies and activities as determined at the site level. | 1.2.5: Hire VAPA certificated elementary prep teachers | Partnership with Human Resources is in process. We will add one Art Prep teacher in 2017-2018.
|  |  | 1.2.3: Determine the academic areas that are most conducive to the various arts integration | Research informs that Arts Integration may be employed in all areas of core instruction. | 1.2.6: Monitor and support VAPA elementary prep teachers | Budget being developed to provide Art Prep with necessary materials and supplies as well as tools for lesson development.
| 1.3 | Provide ongoing professional development | 1.3.1: Poll teachers to determine professional development needs and cultivate a professional development plan | Collect feedback from Professional Development attendees and from Site Liaisons and use that to refine the PD program | 1.3.6: Representatives to State Conferences | Creativity at the Core conferences…..CSSESA Conferences….Prof Arts Conferences
|  |  | 1.3.2: Determine a professional development approach for arts integration in each art discipline for elementary teachers | Work with community partners to provide professional development across arts disciplines. | Present "In House" Conferences with local Professional Groups….Invite elementary teachers to training on how to implement strategies | VAPA Kick-Off Event…..Pizza and Planning….LWOB Arts Integration Institute
|  |  | 1.3.3: Coordinate with community arts agencies to provide professional development in arts integration for elementary teachers | Partnerships with the East Bay Center for Performing Arts, The Richmond Art Center, RYSE, and the Integrated Learning Specialist Program from the Alameda County Office of Education | 1.3.8: Encourage District Festivals by arts discipline. | All Dist Music Fest, Richmond Art Show, Annual WCCUSD Dance Festival, Annual WCCUSD Theater Competition
|  |  | 1.3.4: Conduct regular Arts planning meetings to share best practices and dvelop a database of successful klessons by grade level | Monthly Site Liaison Meetings to share lesson presentations. Data base is in planning stages. | 1.3.9: Provide lists of Professional Conferences to teachers and support attendance whenever possible. | Ongoing
|  |  | 1.3.5: Evaluate effectiveness and revise as needed. | Feedback/evaluation from each PD session and at end of year from Site Liaisons | 1.3.10: Continue to develop professional development opportunities for classroom teachers on an ongoing basis. | Vigorous calendar of PD with community partners and educational institutions.
| 1.4 | Valid and Comprehensive Assessment | 1.4.1: Instruction will be modified and enhanced by valid and comprehensive assessment designed to promote reflective practice and data driven planning to improve academic, cognitive, linguistic, and socio-cultural outcomes for students. | Addressed in ILSP program Course C. Multiple models of assessment presented for teachers to bring back to the sites. | 1.4.3: District wide departments will compile a toolbox of valid assessment practices for regular use in the classroom | To be implemented.
|  |  | 1.4.2: Assessment will be formative and involve verbal interaction, tests, portfolios, and performance tasks. | Ongoing at each site.
| 1.5 | Provide On-Line resources to All Teachers for support of VAPA Curriculum and Instruction. | 1.5.1: Disseminate on-line sources for lesson planning and conceptual support to all teachers | PD and Resource page on District VAPA website | 1.5.4: Include library of viable lessons for each level of arts implementation on website | VAPA Website
|  |  | 1.5.2: Poll Arts Teachers and provide a "best of" list of sites by discipline and concept. | Ongoing | 1.5.5: Online site of all performances and art programs. | VAPA Website
|  |  | 1.5.3: Video "Best Practices" and include on website | To be implemented | 1.5.6: By Discipline, art teachers develop their own design to add sites as needs change. | TBD
| 1.6 | Ensure all students have arts instruction by highly qualified VAPA Teachers. | 1.6.1: Identify teachers that have previously received training and support | Established lists through PD and trainings. | 1.6.7: Incorporate certificated arts teachers into the elementary Teacher Prep Program | Gradual implementation based on availability of teachers.
|  |  | 1.6.2: Support existing sites while adding new site representation. | Ongoing Learning Without Borders program | 1.6.8: Incorporate a guest artist and speaker program throughout PreK-6th grade. | Based on Site Requests and Available funding…supported Red Grammer at Grant, Spirit Dance Presentation.
|  |  | 1.6.3: Establish "Arts Liaison" teacher at each school site | Created fall 2016…ongoing entity
|  |  | 1.6.4: Institute "trainer of trainer" model for skill development and lesson development at the elementary level. | Ongoing implementation from Fall 2016.
|  |  | 1.6.5: provide professional development on arts integration and instruction for elementary teachers | Partnered with ACOE ILSP and East Bay Center LWOB and Richmond Art Center BATYC
|  |  | 1.6.6: Develop a process for Ed Services support of guest artists and artist performances | By Request and funding availability
Grade level | Section | Description | Phase I | Status | Phase II | Status | Phase III | Status
7th - 12th | 1.1 | Develop a cumulative, sequential and culturally relevant VAPA grade 7-12 core curriculum, supported by delivery systems that ensure ALL students have access to quality arts education | 1.1.1: Create a listing or arts courses offered at each secondary school site | Completed yearly | 1.1.5: Provide articulation lists from elementary to middle to high school to identify continuing students | In place in Music. Other disciplines to follow.
|  |  | 1.1.2: Track number of arts courses requested on spring course choice lists | Completed Yearly | 1.1.6: Program students into appropriate level of instruction for A-G requirements | Support provided to secondary admin teams to provide appropriate A-G courses for Arts enirollment in High School.
|  |  | 1.1.3: Increase the number of arts electives offered at the middle school level | In Process. Limited at times due to elective availability. Arts added at HMS, Dance and Drama added at KMS. Orchestra added at Helms.
|  |  | 1.1.4: Create a “Levels Expectations” document that details concepts to be taught at each level of instruction | Completed for Music. Other disciplines to follow.
| 1.2 | Provide ongoing professional development | 1.2.1: Conduct discipline specific meetings each quarter to determine needs and facilitate collaboration and planning of events. | Music, Dance, and Art teachers meet. Theater managers also meet and communicate regularly regarding productions, events, and logistics. | 1.2.4: Encourage planning for District Festivals by discipline | Music, Art, Dance, and Theater have instituted annual collaborative presentations for the District community.
|  |  | 1.2.2: Conduct regular arts planning meetings to share best practices and successful lessons | Monthly Site Liaison Meetings. VAPA KickOff. | 1.2.5: Bring in outside speakers | Supported by school site request based on available funding.
|  |  | 1.2.3: Present “In House” conference with presentations by local professional groups; invite elementary teachers for training on how to implement strategies | VAPA Kick Off Event. Annually in October | 1.2.6 Create protocol for sending representatives to state conferences. | By Request depending on funding availability.
| 1.3 | Provide on-line resources to all teachers for support of VAPA curriculum and instruction | 1.3.1 Disseminate online sources for lesson planning and conceptual support to all teachers | Resource page on the VAPA website listing various Organizations and lesson compilations | 1.3.6: Update lists and website, refine and modify content | Updated monthly or as needed
|  |  | 1.3.2: Poll arts teachers and provide a “best of” list of sites by discipline and concept | Monthly site liaison meetings provide updates on useful websites
|  |  | 1.3.3: Create “Best Practices” web page and include library of viable lessons for each level of implementation | "Lesson Vault" established on Google Drive and shared with site liaisons. "Art it Up" created on Facebook to share lessons and activities. "Art it Up" page on Facebook to share lessons and outcomes.
|  |  | 1.3.4: Online site listing of all performance and art programs | VAPA Calendar regularly updated on the VAPA website.
|  |  | 1.3.5: By discipline, art teachers develop their own design to add websites as needs change. | Regular input by instructors
Focus Area II
Grade level | Section | Description | Phase I | Status | Phase II | Status | Phase III | Status
Pre K-6th | 2.1 | Establish equitable programming across school sites/grade levels | 2.1.1: Determine existing arts programs at each level | Dot chart on VAPA web page. Updated annualy. | 2.1.3: Monitor articulation of arts students from elementary through high school | Annual review Data shared with Superintendent.
|  |  | 2.1.2: Develop one or more arts programs where needed to ensure the existence of arts education at each site | Financial support for art supplies and equipmaent. Support for specific programs by request. | 2.1.4: Monitor number of students completing A-G arts requirements at the high school level | TBC
| 2.2 | Identify supplies necessary to support arts integration and instruction at the elementary level | 2.2.1: Determine materials needed to support classroom teachers in providing arts connections in their lessons | Site Liaisons and Principals collaborate to determine amounts and types of materials by site. | 2.2.4: Provide art carts to each school with art supplies for use by classroom teachers | In the process of identifying potential carts. Supply needs identified annually.
|  |  | 2.2.2: Develop plan for distribution of materials by grade level and school site | Funds distributed at the beginning of the year for site use. | 2.2.5: Replenish supplies as needed
|  |  | 2.2.3: Distribute materials and/or funds prior to August 15 each year | Process has been adopted. | 2.2.6: Explore stand-alone arts curricula for possible use at elementary level | Reviewed different platforms but cost was prohibitive.
| 2.3 | Develop a plan for equitable distribution of materials and equipment among school sites | 2.3.1: Principals determine site level needs for materials and equipment based on staff input | In place with assistance from site Liaisons. | 2.3.4: Monitor, evaluate, and support | Process adjusted as needed.
|  |  | 2.3.2: Resources are assigned to individual sites | Budgeting process.
|  |  | 2.3.3: Artifacts are provided by site indicating use of funds and/or materials and equipment | MUNIS approval process. Tracks items and vendors.
| 2.4 | Monitor use of funds | 2.4.1: Principal or designee provides list of items or services purchased for Arts Education with VAPA funds | MUNIS approval process. Tracks items and vendors. | 2.4.3: Monitor semi-annually | Monitor through MUNIS
|  |  | 2.4.2: Database is kept tracking purchases with intended use of funds | MUNIS approval process. Tracks items and vendors.
Grade level | Section | Description | Phase I | Status | Phase II | Status | Phase III | Status
7th - 12th | 2.1 | Increase the number of arts electives offered at the middle school level: | 2.1.1: Develop a list of the current arts electives offered at the middle school level per the master schedules | Accomplished annually | 2.1.4: Support new sections with professional development and supplies | Individual support for new teachers and professional Development for existing teachers through out the year.
|  |  | 2.1.2: Track student requests for arts electives per choice sheets | Master Schedule review
|  |  | 2.1.3: Identify and schedule credentialed arts teachers to cover needed sections. | Site level. VAPA Coordinator assists as needed.
| 2.2 | Identify baseline levels of supplies necessary to support arts instruction at the secondary level | 2.2.1: Survey teachers and compile a list of necessary materials, supplies, and texts to support each arts discipline | Completed: Sites receive funding based on sections and enrollment. Visual Arts receives Purchase Order to Arts Supply store. | 2.2.4: Update list as elective offerings change | Annual review.
|  |  | 2.2.2: Determine funding needed to support all needs | Budget Development process.
|  |  | 2.2.3: Research alternative funding sources as necessary | Grant applications submitted when appropriate.
| 2.3 | Develop plan for equitable distribution of arts supplies and equipment among secondary school sites | 2.3.1: Develop a protocol for provision of required texts for arts courses | Based on teacher request. As needed. | 2.3.3: Update supplies based on changes in technology | Support offered for Graphic/Digital Arts and Photography.
|  |  | 2.3.2: Distribute available funds to support arts learning at all levels | **** See Above | 2.3.4: Provide textbooks for required courses as needed | Assist upon request by sites/teachers/or departments.
[5 empty] | 2.3.5: Distribute supplemental funds, as available, to all individual school sites | Individual projects funded and surplus distributed.
| 2.4 | Monitor use of funds | 2.4.1: Maintain database of expenditures and purchase orders created in support of arts classes and programs | List of Purchase Orders MUNIS Database updated regularly | 2.4.2: Regular periodic monitoring of accounts | MUNIS Check accounts and PO's quarterly.
Focus Area III
Grade level | Section | Description | Phase I | Status | Phase II | Status | Phase III | Status
Pre K-12th | 3.1 | Build and expand efficient and sustainable methods of communication, district to staff and staff to district | 3.1.1: Establish an e-mail group for each arts discipline | Group e-mail established and updated yearly as needed. | 3.1.5 Monitor and assess effectiveness | Accept suggestions for improvement and implement if appropriate.
|  |  | 3.1.2: Establish an e-mail group for all district arts teachers and administrators | Visual Art teachers created. District Admin list and weekly bulletin utilized. | 3.1.6 Enhance and upgrade technology as capability develops | Moved to Google platform and to Facebook page for distribution of information.
|  |  | 3.1.3: Develop a calendar of events and distribution schedule | Performances and exhibits are listed on the VAPA site calendar.
|  |  | 3.1.4: Establish “Remind” groups for event notification | Information on Remind.com given out to all teachers. Sporadic use.
| 3.2 | Establish and maintain innovative modes of teacher to teacher communication | 3.2.1: Establish Google Drive community of arts teachers and Administrators | Facebook "Art it Up" page open to all. | 3.2.4 Update technology as needed to maintain fluid communication between arts teachers | Google/ Facebook/ e-mail groups
|  |  | 3.2.2: Establish Google Docs to facilitate the sharing of written content | VAPA Lesson Vault established on Google Drive to share plans.
|  |  | 3.2.3: Establish regular discipline specific meetings for secondary VAPA teachers | Music monthly. Dance quarterly. Theater as needed. Art each semester.
| 3.3 | Develop and connect with existing best practices in community outreach and public relations | 3.3.1: Develop Blackboard Connect access and protocol for parent communication | Not available to VAPA dept. | 3.3.4 Incorporate information regarding services and activities of VAPA partners into district VAPA | All PD information is shared. All arts related that come to the VAPA department are passed on to all.
|  |  | 3.3.2: Develop VAPA website to include parent information, lessons and resources for students, e.g. practice protocol, assignments, video help for basic skills | Complete and updated regularly as information changes. | 3.3.5 Each VAPA partner will create links to WCCUSD and other VAPA partners on their respective websites | TBD
|  |  | 3.3.3: Develop protocol with WCCUSD Community Engagement to provide PR support for events and accomplishments | Collaboration with the Communications Dept to produce posters and press releases. Video documantation. | 3.3.6 Monitor and assess effectiveness and develop as needed | Regular collaboration and coverage of events for dissemination to Stakeholders
| 3.4 | Monitoring and assessment | 3.4.1: Develop form for evaluation and feedback regarding quality and effectiveness of communication to all stakeholders | Teacher and principal feedback forms distributed. | 3.4.3 Make adjustments and updates as indicated by the feedback received | Format and scheduling of Liaison meetings have been adjusted for better accessibility. Content upgraded regularly.
|  |  | 3.4.2: Administer survey at least once a year | Annual process.
Focus Area IV
Grade level | Section | Description | Phase I | Status | Phase II | Status | Phase III | Status
Pre K-12th | 4.1 | Collaborate with community partners to achieve the goals of the VAPA plan | 4.1.1: Coordinate with community arts organizations to provide professional development for elementary teachers to assist with integration of the arts into the academic day | partnerships with East Bay Center, Richmond Art Center, Alameda County Integrated Learning Specialist Program, RYSE Center | 4.1.3: Review available professional development resources and align with ongoing needs of teachers in integration of the arts | Design work is an ongoing work between WCCUSD VAPA and our community partners.
|  |  | 4.1.2: Contract with RAC and EPCPA for 2015-2016 school year professional development for arts integration | Completed and updated annually based on services provided.
| 4.2 | Create a process and develop strategies for building relationships with community partners and funding programs offered | 4.2.1: By Dec. 2015, develop a timeline for submission and response to service proposals from outside arts organizations | Attend Events. Participate on Stete County Arts lead meetings. Participate in area events and PD opportunities. | 4.2.5: By Aug. 2016, finalize and create contracts for all outside arts organizations with which the District will be working for the coming year | Current process in place.
|  |  | 4.2.2: By January 2016, implement a review procedure and protocol for evaluation of service proposals from outside Arts Organizations | In Place on an annual basis. | 4.2.5: Identify potential grant opportunities to support a sustainable program | Some small grants have been identified and shared across the District. Larger opportunities still need to be developed.
|  |  | 4.2.3: By June, 2016, outside arts organizations submit contract proposals. | Process instituted
|  |  | 4.2.4: By July, 2016, review and evaluate proposals | in process.
| 4.3 | Identify arts industry partnerships to provide summer internships for teachers and/or students | 4.3.1: Research potential partners | Ongoing | 4.3.3: Develop partnerships | Instituted complete program for Integrated Learning Specialist Traing with ACOE and expanded Richmond Art center PD to two sections.
|  |  | 4.3.2: Begin dialogue with identified resources | Ongoing | 4.3.4: Assess and monitor benefits and gains for both parties | Annual Process.